## Report
| Bug Status | Count
https://demowebshop.tricentis.com/ | New | 12
| Re-Open | 0
| Retest-Failed | 0
| Accepted | 0
| Not a Defect | 0
| Duplicate | 0
| Deferred | 0
| Retest | 0
| Closed | 0
| Suggestion | 0
| Not Reproduce | 0
| Not understood | 0
| Client Review Comments | 0
| Total Number of Bugs | 12

## Bug-List
Defect ID | Date | Module/Page Name | Description | Steps to Reproduce if Required | Status | Environment | AssignedTo | Raised By | Priority | Severity | ScreenShot Number | Testers comments | Developer comments
BUG-01 | 28 Jun,2026 | Login | Login button becomes unresponsive after entering valid credentials. User remains on login page without redirection. | 1. Open Login page. 2. Enter valid email and password. 3. Click Login button | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Functional | High
BUG-02 | 28 Jun,2026 | Wishlist | "Add to Wishlist" button is missing for some products under Books and Computers categories. | 1. Navigate to product page. 2. Observe available actions. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Functional | High
BUG-03 | 28 Jun,2026 | Checkout | Promo code field is not displayed during checkout process. | 1. Add product to cart. 2. Proceed to checkout. 3. Observe checkout page. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Functional | Medium
BUG-04 | 28 Jun,2026 | Product Detail Page | Product page layout breaks on mobile viewport and causes overlapping UI elements. | 1. Open DevTools. 2. Enable mobile mode (375px width). 3. Open product page. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Design | High
BUG-05 | 28 Jun,2026 | Shopping Cart | Guest user shopping cart does not persist after browser session ends. | 1. Open Demo Web Shop. 2. Add any product to the shopping cart as a guest user. 3. Close the browser completely. 4. Reopen the browser and visit Demo Web Shop again. 5. Open the shopping cart. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Functional | Medium
BUG-06 | 28 Jun,2026 | Shopping Cart | Cart accepts quantity values of 0 or negative numbers without validation. | 1. Open the Demo Web Shop website. 2. Add any product to the shopping cart. 3.Navigate to the Shopping Cart page. 4.Locate the quantity input field for the product. 5.Enter 0 or -1 in the quantity field. 6.Click the Update Shopping Cart button. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Functional | High
BUG-07 | 28 Jun,2026 | Search | Search returns inconsistent or empty results for valid product names. | 1. Open the Demo Web Shop homepage. 2. Locate the search box at the top of the page. 3. Enter a valid product name such as Laptop. 4. Click the Search button. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Functional | Medium
BUG-08 | 28 Jun,2026 | Registration | Registration process allows duplicate email registration without clear messaging. | 1. Register a new account using an email address. 2. Log out from the account. Navigate to the Registration page again. 3. Attempt to register using the same email address. 4. Submit the registration form. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Functional | Medium
BUG-09 | 28 Jun,2026 | Product Comparison | "Add to Compare" action gives no visible feedback to user. | 1. Open any product listing page. 2. Click the Add to Compare List option for a product. 3. Observe the page behavior. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Design | Low
BUG-10 | 28 Jun,2026 | Checkout | Order confirmation page missing after successful checkout completion. | 1. Add a product to the shopping cart. 2. Proceed through the checkout process. 3. Complete shipping and payment information. 4. Click Confirm Order or Place Order. 5. Observe the final page. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Functional | High
BUG-11 | 28 Jun,2026 | Registration | Password field lacks strength validation or password strength indicator. | 1.Open the Registration page. 2.Enter a weak password such as: 1 a 123 3. Complete the remaining registration fields. 4. Submit the form. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Requirement Clarification | Medium
BUG-12 | 28 Jun,2026 | Newsletter | Newsletter subscription accepts invalid email formats. | 1. Scroll to the newsletter subscription section in the footer. 2. Enter an invalid email address such as: test@ abc invalidemail 3. Click the Subscribe button. | New | Windows 11 / Chrome Latest | Dev-Team | Hassan | Bug-Functional | Medium
Note on A1: Author: you can enter Defect id in interger for e.g 1,2,3
Note on B1: date format is dd-mm-yyyy or dd-month-yy

## Configuration
Defect Status | Environment | Raised By | AssignedTo | Issue Type | Severity | Module Name | Application Name
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Functional | High | Login | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Functional | High | Wishlist | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Functional | Medium | Checkout | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Design | High | Product Detail Page | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Functional | Medium | Shopping Cart | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Functional | High | Shopping Cart | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Functional | Medium | Search | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Functional | Medium | Registration | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Design | Low | Product Comparison | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Functional | High | Checkout | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Requirement Clarification | Medium | Registration | https://demowebshop.tricentis.com/
New | Windows 11 / Chrome Latest | Hassan | Dev-Team | Bug-Functional | Medium | Newsletter | https://demowebshop.tricentis.com/
Closed
Re-Open
Retest
Not a Defect
Duplicate
Deferred
Retest-Failed
Accepted
Suggestion
Not Reproduce
Not understood
Client Review Comments